Water Quality Log — Online Capture & Dashboard Plan

Custom in-house web application: rollout plan for Peregrine Recreation Center

# 1. Objective

Replace the paper Water Quality Log with a custom web application that pool staff use to capture chemical, circulation, and safety readings each shift, and that gives the Aquatics Director and facility management a live dashboard for monitoring compliance, trends, and out-of-range incidents. A working prototype of the form and dashboard, pre-loaded with a year of synthetic sample data, has already been built for stakeholder review; this document lays out the plan to turn that prototype into a production system that reliably captures real data.

# 2. What the app needs to do

- Digital log entry form covering every field on the current paper log: date/time, pool and facility, FC/TC/CC/pH, Total Alkalinity, Calcium Hardness, Saturation Index, controller pH and HRR, circulation temperature/flow/influent/effluent pressure, TDS, no-flow alarm, drains-visible check, bather count, staff initials, and notes.

- Real-time validation against the approved ranges printed on the current log (FC 1.0–10.0, pH 7.2–7.8, CC < 0.2 ppm, Total ALK 60–180, Calcium Hardness 150–1000, Saturation Index -0.3 to +0.3), with the offending field highlighted immediately.

- Automatic alerting the moment a reading is out of range — the current paper process depends on staff remembering to “contact the Aquatics Director immediately”; the app should send that alert itself (SMS, push notification, or email) and require the Director's electronic sign-off before the flag clears.

- A dashboard with date-range filtering (and quick presets like 7/30/90 days), trend charts for chemical readings and bather counts, summary statistics, and a searchable, exportable table of all readings.

- An audit trail: every entry is timestamped and attributed to the staff member who logged it, and corrections are recorded rather than overwritten.

# 3. Architecture

A standard three-tier web application, sized for a single facility today but structured to add pools or locations later:

- Frontend: a responsive web form and dashboard (what the current prototype demonstrates), usable on a poolside tablet, wall-mounted kiosk, or staff phone.

- Backend API: handles validation, persistence, alerting, and access control (e.g., Node.js/Express or Python/FastAPI).

- Database: relational database (PostgreSQL or MySQL) storing readings, pools/facilities, users, and approved-range configuration per pool.

- Hosting: cloud-hosted (AWS/Azure/GCP) unless IT policy requires on-premises; either way, automated daily backups are required.

- Notifications: integrates with email/SMS (e.g., Twilio) or push notifications for out-of-range alerts.

# 4. Roles & permissions

| Role | Can do |
| --- | --- |
| Pool Operator / Lifeguard | Enter and submit readings for their shift; view their own submission history. |
| Aquatics Director | Everything above, plus: receive out-of-range alerts, review and electronically sign off flagged readings, view the full dashboard. |
| Facility Manager / Compliance | View historical data and export audit-ready reports (CSV/PDF) for health inspections; cannot edit past entries. |
| Admin | Manage users, pools/facilities, and approved-range configuration; full system access. |

# 5. Daily workflow

- Staff member tests the water at the start of shift (and again mid-shift, per current practice) and opens the log entry form on the poolside tablet or kiosk.

- They enter all required readings; the form flags anything out of range before submission.

- On submit, the reading is saved with a timestamp and the staff member's initials.

- If any value is out of range, the app immediately notifies the Aquatics Director and marks the entry “pending review” on the dashboard.

- The Director investigates, takes corrective action, and signs off electronically — closing the loop that today depends on a phone call and a handwritten initial.

- The dashboard updates in real time so the Director and Facility Manager can see trends and open issues across all shifts without pulling the paper binder.

# 6. Data retention & compliance

Most health departments require pool chemical logs to be retained for a set period (commonly 1–3 years) and available on demand for inspection. Confirm the exact requirement with the local health authority before finalizing retention settings. The app should:

- Retain all readings indefinitely by default, with configurable archival after the compliance-required period.

- Support one-click export of a date range as a PDF or CSV formatted like the current paper log, for inspectors who expect that format.

- Keep automated, versioned backups separate from the production database.

# 7. Security & reliability

- Authentication for every user (shared facility login is not sufficient once entries are attributed to individuals); SSO if the facility already has an identity provider.

- Role-based access control as defined in Section 4.

- Encryption in transit (HTTPS) and at rest.

- Offline capture support: if poolside connectivity is unreliable, the form should queue entries locally on the device and sync automatically once back online, so a dead Wi-Fi spot never means a missed log.

# 8. Rollout plan

| Phase | Focus | Estimated duration |
| --- | --- | --- |
| 0. Finalize requirements | Confirm field list, approved ranges per pool, retention period with health authority, and notification channel. Use the existing prototype as the discussion baseline. | 1 week |
| 1. Build MVP | Entry form, database, basic dashboard with date filtering — functionally matching the prototype but backed by a real database instead of a browser. | 4–6 weeks |
| 2. Alerting & access control | Out-of-range notifications, Director sign-off workflow, role-based logins, audit trail. | 3–4 weeks |
| 3. Pilot | Run in parallel with the paper log at one pool to validate accuracy and staff workflow before retiring paper. | 2–4 weeks |
| 4. Staff training | Train lifeguards and operators on the tablet/kiosk workflow; publish a quick-reference guide. | 1 week |
| 5. Full rollout | Retire the paper log, extend to additional pools/facilities if applicable, begin regular compliance exports. | Ongoing |

# 9. Hardware considerations

- A wall-mounted tablet or waterproof-cased device at poolside is the most reliable option for consistent logging; a shared staff phone or laptop in the pool office is a lower-cost fallback.

- Screen should stay logged in to the entry form (kiosk mode) so staff aren't re-authenticating between shifts, while the dashboard remains behind a separate login for management.

# 10. Success metrics

- Percentage of required shift readings actually logged (data completeness), compared against the current paper process.

- Time from an out-of-range reading to Aquatics Director acknowledgement.

- Reduction in missing or illegible log entries found during inspections.

- Staff-reported ease of use versus the paper log.

# 11. What's already built

A working prototype demonstrating the form and dashboard experience described above — including range validation, date-range filtering, trend charts, and a synthetic year of sample readings — is available for review alongside this plan. It is intended as a design reference for Phase 0–1, not the production system itself, since it stores data in the browser rather than a shared database.